## Calendar
Ramadan 2027: the social media calendar, week by week
Every date follows the first day of Ramadan on the Dates sheet. Fill in the yellow columns; week 3 shows an example.
Week | Starts | Ends | Phase | Mood | Main posts that week | Platform | Asset | Owner | Status | Notes
1 | 2027-01-25 | 2027-01-31 | Two weeks before | Getting ready | Wardrobe and home refresh, gifting lists, a teaser of the Eid edit
2 | 2027-02-01 | 2027-02-07 | Two weeks before | Getting ready | First look at the Eid edit, the Ramadan greeting scheduled, delivery dates for Eid announced
3 | 2027-02-08 | 2027-02-14 | First ten days | A new routine | Ramadan greeting on day one, calm at-home scenes, the Eid collection live | Instagram Reels | Eid collection Reel 1 of 4 | Social media lead | Scheduled | Post after iftar
4 | 2027-02-15 | 2027-02-21 | First ten days, then the middle ten from day 11 | A new routine, then convenience | Eid collection Reels, sizing and delivery how-tos
5 | 2027-02-22 | 2027-02-28 | Middle ten days, then the last ten nights from day 21 | Convenience, then Eid preparation | Quieter product posts and behind the scenes, the gift guide ready to post
6 | 2027-03-01 | 2027-03-07 | Last ten nights | Eid preparation at its height | Eid outfits, gift guides, the last order date before Eid, paid push
7 | 2027-03-08 | 2027-03-14 | The last night or two, then Eid | Celebration | The Eid greeting, family portraits, thank-you posts, restock news
The five phases
Phase | Starts | Ends | Mood | What to post | Format
Two weeks before | 2027-01-25 | 2027-02-07 | Getting ready | Home refresh, wardrobe edits, gifting lists, a first look at the Eid edit | Feed carousels, Stories
First ten days | 2027-02-08 | 2027-02-17 | A new routine | Calm family scenes, iftar at home, the Eid collection live | Reels, feed
Middle ten days | 2027-02-18 | 2027-02-27 | Routine and convenience | Quick fixes, delivery, how-to clips, quieter product posts | Stories, short Reels
Last ten nights | 2027-02-28 | 2027-03-08 | Eid preparation at its height | Eid outfits, gift guides, order-by dates | Reels, Stories, paid
Eid week | 2027-03-09 | 2027-03-15 | Celebration | Family portraits, colour, thank-you posts, restock news | Feed, Reels
Formulas:
Starts = Dates!$B4+7*([Week]-3)
Ends = [Starts]+6

## Assets
Ramadan 2027: what to shoot before the month starts
Planning counts assume four or five feed posts and one or two Reels a week for seven weeks. Put your own targets and progress in the yellow columns.
Asset | Planning count | Carries | Your target | Shot so far | Still to shoot
Hero campaign stills | 3 to 5 | Every phase, paid | 4 | 0 | 4
Feed stills, on model and product | 25 to 35 | Feed and shop grid | 30 | 0 | 30
Vertical videos | 8 to 12 | Reels, TikTok, paid | 10 | 0 | 10
Stories frames | 20 to 30 | Daily Stories | 25 | 0 | 25
Iftar or gifting table | 1 set-up, stills and video | First ten days, last ten nights | 1 | 0 | 1
Founder or brand story | 1 short piece | Two weeks before, Eid week | 1 | 0 | 1
Total |  |  | 71 | 0 | 71
Shoot window opens (12 weeks before) | 2026-11-16
Shoot window closes (8 weeks before) | 2026-12-14

## Dates
Ramadan 2027 social media calendar
BlueSky Studio, Al Quoz, Dubai
First day of Ramadan (expected) | 2027-02-08
Days in Ramadan (29 or 30) | 29
First day of Eid Al Fitr | 2027-03-09
Pre-Ramadan posts start | 2027-01-25
Shoot window opens (12 weeks before) | 2026-11-16
Shoot window closes (8 weeks before) | 2026-12-14
How to use
The yellow cells are yours to change. When the UAE announces the start of Ramadan, change B4, and B5 once Eid is announced: every date in the Calendar and Assets sheets follows.
Planning default: 29 days, so Eid falls on the earlier of the two expected dates and your last order date before Eid stays safe.
Source: expected dates projected by the UAE Astronomy Centre, as reported by The National on 6 October 2026. Subject to moon sighting.
The guide that goes with this calendar: https://blueskystudios.ae/en/blog/ramadan-content-calendar-uae